## Strategic Risk Register
STRATEGIC RISK REGISTER
Organization: |  |  |  | Period: |  |  |  | Risk Appetite: |  | Medium |  | Version: |  | 1.0
Risk ID | Strategic Objective | Risk Description | Risk Category | Causes | Consequence | Inherent Likelihood | Inherent Impact | Inherent Score | Inherent Rating | Controls in Place | Control Rating | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Treatment Strategy | Risk Owner | Target Date
STR-001 | Market Growth | Risk of losing market share to competitors | Economic | Competitive pressure | Revenue decline | 3 | 4 | 12 | High | Existing controls | Partial | 2 | 3 | 6 | Tolerable | Treat | Risk Owner | 2026-12-31
STR-002 | Digital Transform. | Risk of failure to implement digital strategy on time | Technological | Resource constraints | Delayed benefits | 4 | 4 | 16 | High | Existing controls | Partial | 3 | 3 | 9 | Tolerable | Treat | Risk Owner | 2026-12-31
STR-003 | Stakeholder Rel. | Risk of damage to key stakeholder relationships | Reputational | Communication gaps | Loss of funding | 2 | 5 | 10 | High | Existing controls | Partial | 1 | 4 | 4 | Low | Treat | Risk Owner | 2026-12-31
STR-004 | Regulatory Env. | Risk of adverse regulatory changes | Legal | Policy uncertainty | Compliance costs | 3 | 4 | 12 | High | Existing controls | Partial | 2 | 3 | 6 | Tolerable | Treat | Risk Owner | 2026-12-31
STR-005 | Talent Strategy | Risk of failing to attract and retain top talent | Strategic | Labour market | Capacity gaps | 3 | 3 | 9 | Tolerable | Existing controls | Partial | 2 | 2 | 4 | Low | Treat | Risk Owner | 2026-12-31